## Slide 1
Status Update: Socio-Cultural Commission [SCC]
Portfolio: IPA Houses
As at 29 September2019

## Slide 2
IPA Hosting Book – Official IPA Houses & Other Accommodation
The Project commenced during 2016 with Version 01 Published during April 2017
Version 11 to be published during October 2019
Status of Hosting Book Project | Completed 100%
Other IPA Accommodation Documented | 226 Facilities of 18 Sections
Official IPA Houses & Apartments Documented in the Hosting Book | 50 Facilities of 18 Sections
Total IPA Facilities Documented (Official & Other) | 276 Facilities of 30 Sections
Newsletter Articles
Articles of Sections Received | 50 = 100%
Articles Published Since March 2016 | 41= 82%
This aspect is fully completed with articles received from all Sections
Articles Still to be Published | 9 = 18%
IPA Sections with Only IPA Houses/Facilities | 18 x Sections
IPA Sections with Only Other IPA Accommodation | 18 x Sections
IPA Sections with BOTH IPA Houses & Other Accommodation | 6 x Sections

## Slide 3
IPA Houses – Status Update of the 2016/2019 Workplan
Activity | Requirement/s | Target Date | Status | Comments
Workplan: Guest House Portfolio | To develop a IPA House Workplan for 2016/2019 | End January 2016 | Finalised | Finalised and approved by the SCC Chairperson - January 2016
Procedures for IPA Houses: Review | To review the Procedures for IPA Houses | 2017 IWC | Finalised | Approved and adopted at the 2017 IWC
Procedures: Hosting Sections Meeting | To develop Procedures for Hosting Sections Meetings which is directed at standardising House Management Meetings under the ISCC | End May 2016 | Finalised | Approved and adopted at the 2017 IWC
Agreement - Other Accommodation | In line with the Procedures for IPA Houses to develop an Agreement Template for use by Sections | End May 2016 | Finalised | Finalised – October 2017
Hosting Section Meeting | Hosting Section Meeting to be arranged | End Sept 2019 | Finalised | Finalised – September 2019 Hosted by Section Romania
News Letter Articles: ** IPA Houses | To monthly have an article about an IPA Guest House placed in the News Letter | Monthly | Ongoing | 38 Articles published since April 2017

## Slide 4
Summary of IPA Facilities per Section
Section | Official IPA Facilities | Other Accommodation
Australia | 2 | 0
Austria | 0 | 4
Belgium | 1 | 0
Brazil | 2 | 0
Botswana | 0 | 1
Canada | 0 | 20
Cyprus | 0 | 10
Denmark | 2 | 0
Finland | 1 | 0
France | 1 | 1
Germany | 13 | 0
Greece | 3 | 0
Hungary | 3 | 22
Ireland | 5 | 0
Israel | 0 | 27
Italy | 0 | 3
Luxembourg | 1 | 0
Malta | 0 | 1
Montenegro | 0 | 12
Netherlands | 1 | 3
New Zealand | 0 | 66
Poland | 0 | 5
Portugal | 4 | 20
Romania | 3 | 0
Serbia | 1 | 0
South Africa | 4 | 16
Spain | 1 | 5
Sweden | 2 | 0
Switzerland | 0 | 10
United Kingdom | 0 | Various Police Homes
Total | 50 | 226

## Slide 5
Thanking
The International President
SCC Chairperson
IEB Members
The IAC Personnel and
All Sections for their contributions, support and guidance
H (Vossie) Vos
SCC Member responsible for IPA Houses
vossie.ipa@gmail.com